## Slide 1: D.Eco Application
Presented by Code Monkey

## Slide 2: Sprint 1 Inception
Use Case Model
Risk Analysis
Technology Plan
Effort Estimate
System Architecture
Code Monkey
April 19, 2017

## Slide 3: Use Case Model
Code Monkey
April 19, 2017

## Slide 4: Technology Plan
Technology | Experience Rating
Phone App Technologies | 
IOS | Tutorial
Android | None
Map Technologies | 
Google Maps | Tutorial
Open Layers | None
OpenStreetMap | None
Code Monkey
April 19, 2017

## Slide 5: Technology Plan
 | Experience Rating
Application & Web Development | 
Java | Small Scale
Swift | Tutorial
HTML 5 | Small Scale
Javascript | Tutorial
Code Monkey
April 19, 2017

## Slide 6: Risk Analysis
Risk | Mitigation
No experience with IOS development | Schedule time and work through tutorials
No experience with Android development | Schedule time and work through tutorials
Limited experience with app development | Schedule time and work tutorials
Team member conflicting schedules | Plan meetings for in advance
No experience accessing GPS in mobile apps | Schedule time to learn and work through tutorials
No experience with utilizing Google Maps in mobile apps | Schedule time to learn and work through tutorials
Code Monkey
April 19, 2017

## Slide 7: Effort Estimate
Screen/Report | Complexity | Object Points | Notes
View Map | 1 | 1 | Screen will be constructed by reading Drury location from the data source.
Take 21 Tree Tour | 2 | 2 | Screen will be constructed by Drury's location and individual location from the data source.
Subscreen |  |  | 
Read About Trees | 1 | 1 | Simple text with some images on screen.
Code Monkey
April 19, 2017

## Slide 8: Effort Estimate Assumptions
Screen/Report | Complexity | Object Points | Notes
3GL Modules |  |  | 
GPS Tour | 1@10 | 10 | Module to find individual location with GPS.
Server Modules | 2@10 | 20 | Data server for all 4 Map Modules.
Total Object Points |  | 34 | Total object points for the project.
Code Monkey
April 19, 2017

## Slide 9: Effort Estimate
Productivity (PROD)
  PROD estimate is normal (10)
  PROD = 160 NOP / 16 person months
  PM = 4hr x 1 week x 4 weeks
  Justification: students
Some code reuse is anticipated so adjusted effort = NOP
  NOP = (160 Obj pts x (100-0.1)) / 100 = 159.8
Effort Estimate in person months (PM) (PM = 16)
Effort(PM) = 159/10 = 15.9 person monthsProductivity (PROD)
  PROD estimate is normal (10)
  PROD = 160 NOP / 16 person months
  PM = 4hr x 1 week x 4 weeks
  Justification: students
Some code reuse is anticipated so adjusted effort = NOP
  NOP = (160 Obj pts x (100-0.1)) / 100 = 159.8
Effort Estimate in person months (PM) (PM = 16)
  Effort(PM) = 159/10 = 15.9 person months
Code Monkey
April 19, 2017

## Slide 10: Initial Architecture
Code Monkey
April 19, 2017

## Slide 11: Security Risk
Penetration Attacks
  Denial of service.
Code Monkey
April 19, 2017

## Slide 12: Elaborating on the Elaboration Plan
Elaboration Architecture:
  During elaboration, we will update the initial architecture to have a better documented architecture.
Create elaboration class diagram:
  Work alongside teammates to create an accurate elaboration class diagram.
Updating the communication diagram:
  Ensuring all communication is documented properly within the diagram.
April 19, 2017

## Slide 13: Plan – Sprint 1 Elaboration
Code Monkey
April 19, 2017
What | Who | When
Update communication diagram | Fisal, Morgan | 4/26/17
Create elaboration class diagram | Cory, Bijan | 4/26/17
Update architecture in Elaboration | Kylie, Cyler | 4/26/17